## DAAN881_Team1_Schedule
Estimated Start | Estimated Finish | Description of Task | Personel Needed | Names: | Started On: | Completed On: | Status
2024-05-09 | 2024-05-12 | Selection of WHAT the problem we are solving | 3 |  |  |  | Not Started
2024-05-09 | 2024-05-12 | Creation of Initial Schedule | 2 | Botzer, | 2024-05-10 |  | On Schedule
2024-05-12 | 2024-05-18 | Completion of Deliverable 1 |  |  |  |  | On Schedule
2024-05-19 | 2024-05-26 | Acquisition of Datasets | 5 |  |  |  | Not Started
2024-05-26 | 2024-06-02 | Initial Inspection, Cleaning, Regularization of Datasets | 3 |  |  |  | Not Started
2024-05-20 | 2024-06-02 | Completion of Deliverable 2 |  |  |  |  | Not Started
2024-06-02 | 2024-06-06 | Initial descriptive statistics of the dataset; Looking at Mitigating Collinearity |  |  |  |  | Not Started
2024-06-06 | 2024-06-12 | Dimensionality Reduction (SVD / PCA) | 2 |  |  |  | Not Started
Not Started
Not Started
2024-06-03 | 2024-06-16 | Completion of Deliverable 3 |  |  |  |  | Not Started
2024-06-17 | 2024-06-30 | Completion of Deliverable 4 |  |  |  |  | Not Started
2024-07-01 | 2024-07-14 | Completion of Deliverable 5 |  |  |  |  | Not Started
2024-07-18 | 2024-07-28 | Completion of Deliverable 6 |  |  |  |  | Not Started
2024-07-18 | 2024-09-05 | Completion of Deliverable 7 |  |  |  |  | Not Started
2024-09-05 | 2024-09-11 | Final Proof Read of Deliverable 7 and Final Submission |  |  |  |  | Not Started

## Sheet2 (hidden)
Not Started
On Schedule
Behind
Complete